## Risk Register
Risk ID | Risk Description | AM_Include
WT-001 | Turbine foundation rework | WT-001
WT-002 | Access road wet-weather damage | WT-002
WT-008 | WTG delivery delay (long-lead) | WT-008
WT-009 | Main crane mobilisation delay | WT-009
WT-020 | HV array cable test failures | WT-020
WT-021 | Grid connection redesign | WT-021
WT-026 | Substation civils delay | WT-026
WT-027 | Substation E&I commissioning slip | WT-027
WT-031 | SCADA integration defects | WT-031
WT-032 | Turbine commissioning faults | WT-032

## AM_Period_Status
Period end | 2026-02-28
Previous period
Project phase | Civil & Foundations
Engine run date
Engine run hash
Analyst | Synthetic Wind PM
Reviewer | Synthetic Wind Reviewer
Period notes | Baseline period. All schedule risks at register baseline; early civil works underway.
Risk_ID | Risk_title | Status_this_period | Status_changed | Probability_current | Probability_override | Owner | Mode_current | Mode_override | Fired_date | Closed_date | Notes_this_period
WT-001 | Turbine foundation rework | Open |  | 0.45 |  | Civil Lead | Series
WT-002 | Access road wet-weather damage | Open |  | 0.5 |  | Civil Lead | Hybrid
WT-008 | WTG delivery delay (long-lead) | Open |  | 0.4 |  | Procurement Lead | Series
WT-009 | Main crane mobilisation delay | Open |  | 0.45 |  | Erection Lead | Hybrid
WT-020 | HV array cable test failures | Open |  | 0.35 |  | Electrical Lead | Parallel
WT-021 | Grid connection redesign | Open |  | 0.3 |  | Grid Lead | Series
WT-026 | Substation civils delay | Open |  | 0.35 |  | Substation Lead | Hybrid
WT-027 | Substation E&I commissioning slip | Open |  | 0.35 |  | Substation Lead | Parallel
WT-031 | SCADA integration defects | Open |  | 0.5 |  | Commissioning Lead | Series
WT-032 | Turbine commissioning faults | Open |  | 0.45 |  | Commissioning Lead | Hybrid

## AM_Milestones
Milestone_ID | Milestone_name | WBS_code | Planned_start | Planned_finish | Status | Percent_complete | Actual_start | Actual_finish | Notes
WM-01 | Foundations complete |  |  | 2026-03-15 | In progress | 0.4
WM-02 | Turbine erection complete |  |  | 2026-04-30 | Not started | 0
WM-03 | Grid connection energised |  |  | 2026-05-31 | Not started | 0
WM-04 | Commissioning complete |  |  | 2026-06-30 | Not started | 0

## AM_Mitigation_Log
Mitigation_ID | Risk_ID | Description | Cost_AUD | Lead_time_weeks | Status | Approved_date | Completed_date | Owner | Estimated_days_saved | Actual_days_saved | Notes