## TOC & Instructions
Cost-QRA Register - project input document
Scaffolded once by tools/register_scaffold.py, then this file is yours - fill it in, it is standalone. Re-scaffolding is never run against a live register.
Register contract |  | The engine checks this on every run and refuses on any mismatch. Shown here from Settings!B6, never typed twice.
Tabs, in the order you fill them (auto-generated from the sheet inventory)
MC_Params | Engine run parameters: day rate, programme seasons, CP threshold, TIC. Fill the day rate or schedule-dollar figures stay zero. Settings holds iterations/seed/view. | you fill
Lists | Cascade lists - edit here; the dropdowns follow. | you fill
Risk Register | Event risks - cost + schedule three-point inputs, EMV. | you fill
Mapping | P6/CPM binding for schedule (Time=Yes) risks. | you fill
Risk_Activity_Patterns | Schedule risk-to-activity patterns - workshop input, you fill this. | you fill
Risk_Pattern_Assignments | Per-risk pattern assignment - workshop input, you fill this. | you fill
Treatments | Per-risk treatments + effectiveness - workshop input, you fill this. | you fill
Methodology | CG correlation coefficients + Mode multipliers. | you fill
Settings | Run settings (iterations/seed/view/prefix); the LIVE run-config surface. | you fill
Layer1_Base | Layer-1 base estimate matrix. | you fill
Layer1_Factors | Layer-1 risk factors. | you fill
Layer1_Allocation | Layer-1 factor x WBS allocation. | you fill
Layer1_Correlation | Layer-1 factor correlation matrix. | you fill
Summary | SRA calibration comparators 1 and 2 - CALCULATED from the register, do not type. | calculated
EMV & Mode Analysis | Deterministic Layer-1 EMV + Mode charts. | calculated
Simulation | Model write-back: P-curve, S-curve, convergence. | model writes
Reference (xlwings) | xlwings requirements + @script (paste-once). | reference
Cell-type legend
input | Blue font, unlocked - you fill this in.
calc | Black font, locked - a live Excel formula (do not overwrite).
model | Amber fill - written by the model each run; do not edit.
model-read | Thin blue border - the Python model reads this cell (may also be an input).
Methodology defaults
The Methodology tab ships with CG coefficients defaulted to 0.5 - review / elicit per project. Mode multipliers (Series 1.0 / Hybrid 0.5 / Parallel 0.0) are locked methodology constants.
Layer 1 - deterministic factor model (optional)
The four Layer1_* tabs and the EMV & Mode Analysis tab are STANDARD on every register, but Layer 1 ships OFF: Settings!Set_Layer1_Enabled = FALSE, so the blank grids have NIL impact and the register reads exactly as a cost-only project. The grids ship at their real shape, blank: Layer1_Base is 12 placeholder WBS rows x 8 resource columns, in $M; Layer1_Allocation is 25 factor rows x the same WBS columns; Layer1_Correlation is a 25-factor lower triangle. To use Layer 1: (1) on Layer1_Base rename the WBS rows you need and type each row's $M by column, then the Declared_Total. A row with no numbers is ignored, so type 0 for a genuine zero. (2) On Layer1_Allocation rename the same WBS columns to match Layer1_Base EXACTLY - the model matches the two by name and refuses a mismatch; unused placeholder columns can stay. List your factors on Layer1_Factors (pick names from the dropdown) and tick their WBS cells with x. (3) On Layer1_Correlation type the correlated factor names across row 4 and down column A in the same order, and the coefficients in the blue lower triangle; grey cells are never read, and a blank pair means 0. (4) ONLY THEN set Set_Layer1_Enabled = TRUE. Turning Layer 1 on before the grids are filled is refused with a message naming the tab. The EMV & Mode Analysis tab (totals + charts) populates from the register EMV columns whenever the register is filled or a run happens. Leave the flag FALSE to keep Layer 1 off. A project needing more rows regenerates with build_template(n_layer1_wbs_rows=, n_layer1_factors=).
Sheet protection (REG04)
The machine tabs are protected (no password): input cells are unlocked, the contract cells + formulas are locked, and the workbook structure is locked so tabs cannot be deleted/reordered. This guards against accidental edits - it does NOT stop you deleting a named range, so run Validate Contract after any structural edit. That is a task-pane item, not a button on any sheet, and it exists only after activation - see 'Running a simulation' below. To make deliberate changes, Review > Unprotect Sheet.
Running a simulation
STEP 1 - ACTIVATION, ONCE PER WORKBOOK, AND IT IS A SPECIALIST'S TASK (R-8). As it ships this workbook holds no code and no buttons: there is nothing to press and nothing is broken. A risk specialist installs the xlwings Lite add-in, adds numpy and scipy to its Environment, generates the model script by running tools/make_qra_xlwings.py in the repository, and pastes the result into the xlwings Lite editor. The Reference (xlwings) tab carries the requirements and a readable copy of the entry points. Until this is done, no simulation can run.
STEP 2 - FILL THE REGISTER. Enter one risk per row on Risk Register from row 5. Blue cells are yours; the dropdowns are driven by the Lists tab. You can sort and filter the register with the sheet protected. You cannot INSERT a row: Excel inserts a whole row and the EMV columns are locked calc cells, so a 41st risk means Review > Unprotect Sheet (a specialist's step) or a register regenerated at a higher row count. Set the run controls on Settings (iterations, seed, view). If you are dollarising schedule delay, put the day rate on MC_Params - it is blank as shipped, and every schedule-dollar figure stays zero until it is filled.
STEP 3 - RUN, from the xlwings Lite task pane on the right. These are task-pane items, NOT buttons on any sheet: 'Run Simulation' (the interactive count from Settings), 'Run Simulation 100k' (the deliverable count), and 'Validate Contract' (self-checks the named ranges and the version, writing PASS or FAIL). Results land on the Simulation tab, which is amber - written by the model, do not edit.
WITHOUT ACTIVATION you can still do real work: fill the register and read the live expected-value totals and charts on Summary and EMV & Mode Analysis. Those are ordinary Excel formulas and need no simulation. What activation adds is the Monte-Carlo run.
SPECIALIST TABS. The four Layer1_* tabs are Tier-2: they need an elicited factor model and are optional (see Layer 1 above). Simulation and Out_* are written by the model. A generalist needs none of them.
Units, basis and formats - read before filling
UNITS. Risk Register costs are dollars ($); time is working days. Probability and Probability (Time) are FRACTIONS between 0 and 1: 0.45 means 45%, and entering 45 makes the risk fire on every iteration, silently. Layer-1 base values and Declared_Total are $M.
BASIS. Every figure is contingency at base date, before escalation. Escalation (GN4) is applied downstream to reach an outturn figure, never in this workbook.
THREE-POINT INPUTS. Optimistic / Most Likely / Pessimistic are read by the Distribution column. Triangular and PERT treat Optimistic and Pessimistic as absolute bounds. Lognormal treats them as roughly P10 and P90 with a tail beyond Pessimistic, and Most Likely as the median. Binary fires the Most Likely value; Binary/PERT draws a PERT when it fires. The time three-points follow the same rule, in working days.
COMPOSITION. Each iteration fires each risk with MC Include = Yes against its Probability and sums the sampled costs - MC Include is the switch, not Risk Status. A Time Impact = Yes risk shares one severity draw between its cost and its delay, so the two move together. When Layer 1 is on, each base cell is multiplied by (1 + factor) for every factor bound to it (rows via Layer1_Allocation, columns via Column_Scope) - the factor three-points are proportional deltas, 0.05 meaning +5% - and the result is added to the event total.
RECORDED, NOT READ. Effectiveness_Confidence, Default_Mapping_Confidence and Assignment_Confidence are kept for a reviewer and never used by the engine: any scale, or blank.
WHERE THE REST IS. Each fillable sheet carries its notes above its headers and each column's format on its header cell (hover). How to run: 'Running a simulation' above. What the colours mean: the legend above.
Project identity
Project name
Project number
Client
Prepared by
Revision | A
Issue date

## Risk Register
Blue cells from row 5 are yours; black cells are labels or live formulas. Hover a column header for its format. Units, basis and the three-point conventions are on TOC & Instructions.
Probability is a FRACTION (0.45 = 45%). Costs are dollars, time is working days, both contingency at base date before escalation. Time Impact = Yes rows need a Mode and a Mapping row.
[13 empty] | Contingent Risk Cost | [5 empty] | Time (Working Days) | [5 empty] | Analyst / Derived (deterministic Layer 1) |  |  |  |  | Schedule Binding (P6-ready)
Risk ID | Risk Status | Risk Description | Package | RBS LVL 1 | RBS LVL 2 | MC Include | Distribution | Correlation Group | Recurrence Type | Causes | Consequences | Existing Controls | Cost Impact | Probability | Optimistic ($) | Most Likely ($) | Pessimistic ($) | Basis of Estimate | Time Impact | Probability (Time) | Optimistic (days) | Most Likely (days) | Pessimistic (days) | Basis of Estimate | Mode | Impact_Basis | EMV_cost ($) | EMV_sched_days | EMV_sched_dollars ($) | Schedule Activity ID (P6)
Note on H4: Chooses how the three-point estimate is read. Triangular and PERT treat Optimistic/Pessimistic as ABSOLUTE BOUNDS; Lognormal treats them as roughly P10/P90 with a tail beyond Pessimistic, and Most Likely as the median. One of: Triangular, PERT, Binary, Binary/PERT, Lognormal.
Note on O4: A FRACTION between 0 and 1, not a percentage. 0.45 means 45%. Entering 45 makes the risk fire on every iteration, silently.
Note on P4: Cost if the risk occurs and goes well. Its meaning depends on Distribution: a bound under Triangular/PERT, roughly the P10 under Lognormal. This is the cost GIVEN the risk occurs — the probability is applied separately.
Note on Q4: The modal cost given the risk occurs. Under Lognormal this is the median.
Note on R4: Cost if the risk occurs and goes badly. A bound under Triangular/PERT; roughly the P90 under Lognormal, which samples beyond it.
Note on T4: Yes if this risk also delays the schedule. A Yes row must carry a Mode and a row on the Mapping sheet, or the schedule arm cannot bind it. One of: Yes, No.
Note on U4: A fraction between 0 and 1, as for Probability. 0.45 means 45%.
Note on Z4: How the delay combines with others. Required on every Time Impact = Yes row; the build fails without it. One of: Series, Hybrid, Parallel.

## Lists
Cascade lists - edit here; the Risk Register dropdowns follow.
Distribution | MCInclude | TimeImpact | Recurrence | Mode | CGCode | RBS_L1 | RBS_L2 | Package | Factor
PERT | Yes | Yes | Single | Series | CG01 | Technical | Design | Civil | Labour rate
Triangular | No | No | Recurring | Hybrid | CG02 | Commercial | Construction | Structural | Material rate
Lognormal |  |  | None | Parallel | CG03 | Management | Procurement | Mechanical | Plant rate
Binary |  |  |  |  | CG04 | External | Interface | Electrical | Productivity
Binary/PERT |  |  |  |  | CG05 | Environmental | Approvals | Piping | Quantity growth
[5 empty] | CG06 | Delivery | Weather | Instrumentation | FX
[5 empty] | CG07 |  | Ground Conditions | Commissioning | Escalation
[5 empty] | CG08 |  | Commissioning | Management
CG09
CG10
CG11
CG12
CG13

## Mapping
P6/CPM binding for schedule (Time=Yes) risks. Blue cells are yours. The header row is the contract and is locked; hover a header for its format. Units and basis: TOC & Instructions.
Prefix_List: ONE activity-code prefix, despite the column name — e.g. `20.` to bind every activity whose code starts with 20, or a full code to bind exactly one. A trailing dot is stripped. Blank = the risk binds nothing and contributes no delay.
Injection_Method: How the sampled delay is applied to the bound activities. One of: additive_pert_days, discrete_event_additive_days, productivity_multiplicative_factor. Blank = use the register default, Methodology!Default_Injection_Method.
Gating_Activity_ID: The single activity this risk gates, as it appears in the schedule. An ID that names no activity is SKIPPED, not guessed — the risk then falls back to the programme profile with nothing on screen saying so.
Risk ID | Pattern_ID | Prefix_List | Activity_Count | Gating_Activity_ID | Injection_Method
Note on C6: ONE activity-code prefix, despite the column name — e.g. `20.` to bind every activity whose code starts with 20, or a full code to bind exactly one. A trailing dot is stripped. Blank = the risk binds nothing and contributes no delay.
Note on E6: The single activity this risk gates, as it appears in the schedule. An ID that names no activity is SKIPPED, not guessed — the risk then falls back to the programme profile with nothing on screen saying so.
Note on F6: How the sampled delay is applied to the bound activities. One of: additive_pert_days, discrete_event_additive_days, productivity_multiplicative_factor. Blank = use the register default, Methodology!Default_Injection_Method.

## Risk_Activity_Patterns
Schedule risk-to-activity patterns - workshop input, you fill this. Blue cells are yours. The header row is the contract and is locked; hover a header for its format. Units and basis: TOC & Instructions.
Default_Mapping_Confidence: Free text — any scale you like, or leave it blank. Nothing in the engine reads it; it is provenance for whoever reviews the mapping. Blank = nothing; the engine does not read this column.
Pattern_ID | Description | Prefix_List | Is_Cost_Only | Default_Mapping_Confidence | Reconciliation_Treatment | Example_Risk_IDs | Notes
Note on E4: Free text — any scale you like, or leave it blank. Nothing in the engine reads it; it is provenance for whoever reviews the mapping. Blank = nothing; the engine does not read this column.

## Risk_Pattern_Assignments
Per-risk pattern assignment - workshop input, you fill this. Blue cells are yours. The header row is the contract and is locked; hover a header for its format. Units and basis: TOC & Instructions.
Assignment_Confidence: Free text, as for Default_Mapping_Confidence. Read into the frame and never used in a calculation. Blank = nothing; the engine does not read this column.
Risk_ID | Pattern_ID | Assignment_Confidence | Notes
Note on C4: Free text, as for Default_Mapping_Confidence. Read into the frame and never used in a calculation. Blank = nothing; the engine does not read this column.

## Treatments
Per-risk treatments + effectiveness - workshop input, you fill this. Blue cells are yours. The header row is the contract and is locked; hover a header for its format. Units and basis: TOC & Instructions.
Effectiveness_Pct: A PERCENTAGE: enter 30 for 30%. The engine also accepts a 0-1 fraction and splits the two at 1.0 — so 1.0 is read as 1%, NOT as fully effective. Enter 100 for a fully effective treatment.
Effectiveness_Confidence: Free text. Record how firm the effectiveness estimate is, in your own words.
Risk_ID | Treatment_Description | Effectiveness_Pct | Effectiveness_Confidence
Note on C5: A PERCENTAGE: enter 30 for 30%. The engine also accepts a 0-1 fraction and splits the two at 1.0 — so 1.0 is read as 1%, NOT as fully effective. Enter 100 for a fully effective treatment.
Note on D5: Free text. Record how firm the effectiveness estimate is, in your own words.

## Summary
Total EMV days (PERT) | CALCULATED - live formulas over the Risk Register (the SRA calibration comparators). Do not type; edit the register.
Total EMV $ cost-of-delay (PERT)
Aggregate finish-date slippage days (PERT)
Aggregate finish-date slippage $ (PERT)

## MC_Params
Iterations (n)
Random seed - legacy cost MC only (0=random; the deliverable's seed is SR9_SEED)
Stakeholder view
Reporting P-Level (pct)
TIC - Total Installed Cost ($)
Cascade enabled
Cascade slip rate
Cascade slip cap
Cascade cost scale
day_rate ($/wd)
programme_seasons
cp_hybrid_float_threshold_days
schedule duration (weeks)
expected_time_yes_count

## EMV & Mode Analysis
EMV & Mode Analysis - this project
Deterministic Layer-1 expected values (means) from the register EMV columns, NOT Monte-Carlo P-levels. Live formulas; refresh on open.
DERIVED - populated from the register's EMV columns whenever it is filled or a run happens. Do not type.
Layer-1 totals
Total cost EMV ($)
Total schedule EMV ($)
Total Layer-1 EMV ($)
Risks: Series / Hybrid / Parallel
Risk | Cost EMV ($)
Risk | Schedule EMV ($)
Layer | EMV ($)
Cost
Schedule

## Layer1_Base
WBS Row | Staff | Labour | Plant | Concrete | Steel | General | Subcontract | Provisional
WBS-01
WBS-02
WBS-03
WBS-04
WBS-05
WBS-06
WBS-07
WBS-08
WBS-09
WBS-10
WBS-11
WBS-12
Declared_Total ($M)
Units | $M (read x 1,000,000 -> dollars)

## Layer1_Factors
Factor | Driver | Opt_P10 | ML_mode | P90 | Column_Scope

## Layer1_Allocation
Factor | WBS-01 | WBS-02 | WBS-03 | WBS-04 | WBS-05 | WBS-06 | WBS-07 | WBS-08 | WBS-09 | WBS-10 | WBS-11 | WBS-12

## Layer1_Correlation
Corr_Mode | elicited | (zero ¦ elicited ¦ one)
PSD_Status | valid | (reader recomputes via Corr_flag)
Factor

## Methodology
CG code / Mode | Coefficient / Multiplier | Description
CG01 | 0.5
CG02 | 0.5
CG03 | 0.5
CG04 | 0.5
CG05 | 0.5
CG06 | 0.5
CG07 | 0.5
CG08 | 0.5
CG09 | 0.5
CG10 | 0.5
CG11 | 0.5
CG12 | 0.5
CG13 | 0.5
Series | 1
Hybrid | 0.5
Parallel | 0
Cost_Calibration_Tolerance_Dollars | 50000 | Cost cross-check: absolute tolerance ($)
Cost_Calibration_Tolerance_Pct | 0.001 | Cost cross-check: relative tolerance (fraction)
Schedule_Calibration_Tolerance_Days | 1 | Schedule cross-check: absolute tolerance (days)
Schedule_Calibration_Tolerance_Pct | 0.05 | Schedule cross-check: relative tolerance (fraction)
Schedule_Top3_Tie_Tolerance_Pct | 0.02 | Schedule top-3 cross-check: two contributors the arms rank apart are one tie when within this fraction of each other in BOTH arms
Default_Injection_Method | discrete_event_additive_days | Dual-coded risks with no Injection_Method on the Mapping sheet take this

## Settings
Iterations (interactive default) | 25000
Random seed | 42
View (owner ¦ shared-pool) | owner
Risk-ID prefix | RSK
Iterations (100k on-demand button) | 100000
Contract version | 1.4
Pyodide runtime pin | 314.0.1
Layer 1 enabled (TRUE/FALSE) | FALSE

## Simulation
P-level | Cost ($) | Cum. prob | Cost ($) | Corr_flag | P-level | rho=0 | elicited | rho=1 | Contract validation
P80 CI half-width (25k)
P80 CI half-width (%)
Amber cells are written by the model (xlwings) - do not edit.
MODEL-WRITTEN - do not type on this sheet. Every cell here is overwritten on each run.

## Reference (xlwings)
xlwings Lite - requirements & code (paste-once)
REFERENCE - the paste-once script and its requirements. Nothing to fill.
Requirements (xlwings Lite -> Environment)
numpy
scipy
Pyodide runtime: 314.0.1 (ratified Q4; do not float)
How to load the model code
Generate the pasteable script with python tools/make_qra_xlwings.py -> dist/qra_xlwings_combined.py, then paste it into the xlwings Lite editor. That generated file is the source of truth (byte-parity gated to the repo engine); do not hand-edit. The text below is a human-readable convenience copy of the @script entry points only.
Buttons (xlwings Lite task pane - one per @script)
Run Simulation | cost-QRA at the interactive count (Settings B1 / Set_iterations, default 25,000).
Run Simulation 100k | cost-QRA at the on-demand 100,000 count (Settings B5 / Set_iterations_max) - the deliverable run.
Validate Contract | self-check the named-range contract + version + methodology; writes PASS/FAIL to Out_validation.
src/tier1_xlwings_shell.py (@script source - convenience copy)
"""QRAXL-01 Tier-1 xlwings Lite shell (front-end I/O layer).
The @script entry point the xlwings Lite runtime calls with the open workbook.
It reads the contract-v2 register via xlwings ranges, feeds the cell GRIDS to the
SHARED parser (``qra_register_parse`` - the same one Tier 2 uses, so Tier-1 ==
Tier-2 on the read side by construction), then runs ``qra_core`` and writes the
P-curve back.
The @script is a THIN I/O wrapper over the headless-testable
``tier1_headless.run_headless`` (read ranges -> call the headless run -> write
ranges), mirroring RF-01 (rf_headless.py is the runner, shell_xlwings.py the
I/O). CI covers the compute + formatting; only the literal xlwings range read/
write is Excel-only. ``qra_core``, the parser and the resolver stay Pyodide-
clean; only THIS shell imports xlwings.
"""
from __future__ import annotations
import xlwings as xw
from xlwings import script
from src.qra_register_parse import RISK_REGISTER_SHEET, _LAYER1_SHEETS
from src.register_contract import (
LAYER1_ENABLED_NAME, check_contract, layer1_enabled_flag,
)
from src.rng_streams import SEED_DRAWN, resolve_seed
from src.tier1_headless import METHODOLOGY_SHEET_TITLE, run_headless
# ---------------------------------------------------------------------------
# xlwings Lite COMPATIBILITY (this class of defect cannot be caught headless)
# ---------------------------------------------------------------------------
# xlwings Lite's Office.js backend does NOT implement several classic xlwings
# Sheet APIs. The Tier-1 shell MUST NOT use any of these (they raise a
# base-class NotImplementedError only at runtime in Excel - the headless gates
# read via openpyxl and never exercise them):
#
# FORBIDDEN in Lite: sheet.used_range (xlwings-lite discussion #19)
# sheet.copy()
# sheet.api / Office.js getUsedRange (`.api` unsupported)
#
# SUPPORTED reads/writes used here: named ranges via book.names[nm].
# refers_to_range (Set_*, Out_*, Grid_RiskRegister, Grid_Methodology), and a FIXED
# A1-anchored address read via book.sheets[name].range("A1:..") (Office.js getRange -
# NOT getUsedRange). The grids are anchored at $A$1 (the parser uses ABSOLUTE Excel
# row indices, so the grid must be row-1-aligned).
#
# REG05-A2-FIX (D1): the Layer-1 sheets are read via their whole USED RANGE (a
# generous fixed A1 block, see _sheet_grid), NOT the fixed Grid_Layer1_* names. The
# Grid_Layer1_* names are sized to the empty template's header-only shell and do NOT
# grow when the user fills the sheets, so a name-read saw only the shell (base sum
# 3.9M != declared 50M, 0 factors, empty allocation). The used-range read grows with
# the fill and matches tier1_headless.extract_grids_openpyxl. The Grid_Layer1_* names
# stay EMITTED (contract v1.4 / Validate) - a contract surface, just not the read
# source. Not .expand() (truncates at the V5 layout's interior blank rows) and not
# .used_range/.api (Lite-forbidden); the parser trims trailing blanks, so an
# over-extended fixed block is harmless.
_GRID_NAMES: dict[str, str] = {
RISK_REGISTER_SHEET: "Grid_RiskRegister",
METHODOLOGY_SHEET_TITLE: "Grid_Methodology",
}
# Fixed A1-anchored block for the Layer-1 used-range read (rows x cols). Must
# comfortably exceed any realistic Layer-1 extent (cost columns, WBS rows, factors -
# a compact factor model, never a large table); the parser trims trailing blanks.
# Parked robust option (brief §2.1): dynamic OFFSET Grid_Layer1_* names.
_LAYER1_READ_RANGE = "A1:AX200" # AX = col 50; 200 rows
def _range_grid(book, range_name: str):
"""Read a named range's values as a 2D grid (list of row-lists). Returns []
if the named range is absent. Lite-safe (named-range read only)."""
try:
rng = book.names[range_name].refers_to_range
except (KeyError, Exception): # noqa: BLE001 - Lite raises varied types on a missing name
return []
v = rng.value
if v is None:
return []
if not isinstance(v, list):
return [[v]] # single cell
if v and not isinstance(v[0], list):
v = [v] # xlwings collapses a single row to 1D; re-wrap to 2D
return v
def _sheet_grid(book, sheet_name: str):
"""Read a whole Layer-1 sheet as a 2D grid over a generous FIXED A1-anchored
block (:data:`_LAYER1_READ_RANGE`). Lite-safe: an explicit address via
``book.sheets[name].range(addr)`` (Office.js getRange), never the Lite-forbidden
whole-sheet readers listed in this module's header. Grows with the user's fill
where the fixed ``Grid_Layer1_*`` name would not (REG05-A2-FIX D1); the parser
trims trailing blanks, so over-covering is harmless. ``[]`` if the sheet absent."""
try:
sht = book.sheets[sheet_name]
except (KeyError, Exception): # noqa: BLE001 - Lite raises varied types when absent
return []
try:
v = sht.range(_LAYER1_READ_RANGE).value
except Exception: # noqa: BLE001 - a missing/empty sheet range reads as nothing
return []
if v is None:
return []
if not isinstance(v, list):
v = [[v]] # single cell
elif v and not isinstance(v[0], list):
v = [v] # xlwings collapses a single row to 1D
# trim trailing all-blank rows so the grid matches the openpyxl used range.
while v and all(c is None for c in v[-1]):
v.pop()
return v
def read_grids_xlwings(book) -> dict:
"""Tier-1 grid extraction (the Lite-safe analogue of
``tier1_headless.extract_grids_openpyxl``). Risk register + methodology via their
``Grid_*`` named ranges (sized to extent at build); the Layer-1 sheets via their
whole USED RANGE (:func:`_sheet_grid`, REG05-A2-FIX D1). Same grids, same parser.
A client register with no Layer-1 sheets -> ``layer1={}`` -> Layer 1 OFF, as Tier 2.
REG05-A2 §3.2: read ``Set_Layer1_Enabled`` and thread it in as
``layer1_enabled``; when not TRUE, pass ``layer1={}`` so the shared parse gate
returns None (an empty, present-but-disabled Layer-1 is a read no-op)."""
enabled = layer1_enabled_flag(_named_value(book, LAYER1_ENABLED_NAME))
layer1 = (
{
sheet: _sheet_grid(book, sheet)
for sheet in _LAYER1_SHEETS
if _sheet_grid(book, sheet)
}
if enabled else {}
)
return {
"risk_register": _range_grid(book, _GRID_NAMES[RISK_REGISTER_SHEET]),
"layer1": layer1,
"layer1_enabled": enabled,
# GD-B: the register's own methodology surface (CG coeffs + mode
# multipliers). Absent -> [] -> the resolver fails loud (no fallback).
"methodology": _range_grid(book, _GRID_NAMES[METHODOLOGY_SHEET_TITLE]),
}
def _named_value(book, name):
"""Read a named-range scalar value (Lite-safe). Returns None if absent."""
try:
return book.names[name].refers_to_range.value
except Exception: # noqa: BLE001 - Lite raises varied types on a missing name
return None
def _pad(rows2d: list, nrows: int, ncols: int) -> list:
"""Truncate/pad a 2D list to (nrows, ncols) with None so the write matches
the fixed named-range shape (RF-01 pattern)."""
out = []
for i in range(nrows):
row = list(rows2d[i]) if i < len(rows2d) else []
out.append([(row[j] if j < len(row) else None) for j in range(ncols)])
return out
def _run_and_write(book, iterations_name: str, default_iter: int):
"""Shared run path for the run buttons: read Set_* ranges -> run_headless ->
write Out_* ranges. ``iterations_name`` selects which Settings cell drives the
iteration count (Set_iterations = interactive default; Set_iterations_max =
the 100k button). Named-range reads/writes only (Lite-safe)."""
grids = read_grids_xlwings(book)
def R(nm):
return book.names[nm].refers_to_range
def _named(nm, default):
try:
return R(nm).value
except Exception:
return default
n_iter = int(_named(iterations_name, default_iter) or default_iter)
# SEEDZERO-01 P5: a stated seed is used as given; blank or 0 is drawn here and written back
# below, so the workbook records the seed its outputs came from. A fraction is refused, not
# truncated. The range is contract-required: without it a drawn seed has nowhere to be
# recorded, so a missing one is refused rather than run unrecorded.
try:
seed_range = R("Set_seed")
except Exception:
raise ValueError(
"Set_seed is missing. It is required by the register contract, and it is where a "
"drawn seed is recorded: restore it (Settings!B2), blank or 0 for a random run."
) from None
seed, seed_source = resolve_seed(seed_range.value, where="Set_seed")
view = str(_named("Set_view", "owner") or "owner").strip().lower()
# GENERIC-01: no fallback. `Set_risk_prefix` is contract-required, and defaulting it to the
# wind project's "WT" meant a register that omitted it had every risk row read against another
# project's prefix, matched none, and returned an EMPTY result rather than an error - a wrong
# answer where the missing range should have been a refusal.
prefix = str(_named("Set_risk_prefix", "") or "").strip()
if not prefix:
raise ValueError(
"Set_risk_prefix is missing or empty. It is required by the register contract and "
"there is no default: a prefix borrowed from another project would match no risk "
"rows and report an empty register as though it were a result.")
# The ENTIRE compute + formatting is the headless core (CI-covered). This
# wrapper only reads the ranges above and writes the ranges below.
out = run_headless(grids, risk_id_prefix=prefix, n_iter=n_iter, seed=seed, view=view)
# First write: if a later output write fails, the outputs already in the sheet still name
# the seed they came from.
if seed_source == SEED_DRAWN:
seed_range.value = seed
R("Out_ptable").value = _pad(out["p_table"], 19, 2)
R("Out_scurve").value = _pad(
list(zip(out["s_curve"]["prob"], out["s_curve"]["value"])), 101, 2
)
R("Corr_flag").value = out["corr_flag"]
conv = out["convergence_note"]
R("Out_conv_halfwidth").value = round(conv["p80_ci95_half_width"], 2)
R("Out_conv_pct").value = round(conv["p80_ci95_half_width_pct"], 4)
if out["triple"]:
modes = ("zero", "elicited", "one")
triple_rows = [
[out["triple"]["elicited"][i][0]] + [out["triple"][m][i][1] for m in modes]
for i in range(len(out["triple"]["elicited"]))
]
R("Out_triple").value = _pad(triple_rows, 19, 4)
@script
def run_simulation(book: xw.Book): # pragma: no cover - exercised in Excel (6b load test)
"""BUTTON: run the cost-QRA at the interactive iteration count (Settings B1 /
Set_iterations, default 25k) and write the P-curve/S-curve/convergence back."""
_run_and_write(book, "Set_iterations", 25_000)
@script
def run_simulation_100k(book: xw.Book): # pragma: no cover - exercised in Excel
"""BUTTON: run the cost-QRA at the on-demand 100k count (Settings B5 /
Set_iterations_max, default 100k) - the high-resolution run for the deliverable.
Same write-back as run_simulation; only the iteration count differs."""
_run_and_write(book, "Set_iterations_max", 100_000)
@script
def validate_contract(book: xw.Book): # pragma: no cover - exercised in Excel
"""REG03 S2 rider (1): a contract self-check for a scaffold-once handover.
After a user hand-edits the scaffolded register, this verifies the
Grid_*/Set_*/Out_* named ranges are all present, Set_ContractVersion matches,
and Grid_Methodology carries its 13 CG + 3 mode rows - writing PASS/FAIL + a
human-readable message to the Out_validation range. A thin I/O wrapper over the
headless ``check_contract`` (CI-covered); it reads via named ranges only, so it
obeys the Lite forbidden-API list documented in this module's header."""
grids = read_grids_xlwings(book)
try:
present = [nm.name for nm in book.names]
except Exception:
present = []
def _named(nm, default=None):
try:
return book.names[nm].refers_to_range.value
except Exception:
return default
ok, message = check_contract(present, grids["methodology"],
_named("Set_ContractVersion"))
book.names["Out_validation"].refers_to_range.value = [
["PASS" if ok else "FAIL"], [message]]